## Folha1
| Start date | Duration
Create VM and setup env | 2020-02-17 | 3
Study interpreter | 2020-02-20 | 16
Experiment interpreter changes | 2020-03-06 | 5
Design modifications architechture and procedures | 2020-03-15 | 5
Develop and implement modifications | 2020-03-22 | 23
Display informatiuon in Shiny application | 2020-04-17 | 3
Prototype final shiny interface | 2020-04-22 | 4
Implement final shiny interface | 2020-04-27 | 18
Test application | 2020-05-15 | 5
Test application with users | 2020-05-20 | 2
Correct user pointed problems | 2020-05-22 | 8
Report and documentation | 2020-05-31 | 30